## Sheet1
Week | Developer | Data Analyst | Business Analyst + Tester | Report Writer + Developer
Week 1 – Project Planning | Set up development environment and GitHub repository | Research travel datasets and available data sources | Research project idea, identify user needs and prepare initial requirements | Research similar travel websites and document project background
Week 2 – Requirements & Design | Review technical requirements and plan system structure | Identify required dataset fields and data requirements | Create SRS, functional & non-functional requirements, user stories | Prepare BRD/project documentation and initial system description
Week 3 – System Design | Design website structure, pages and navigation | Clean and organise initial travel dataset | Create use cases, acceptance criteria and requirements traceability | Prepare system design documentation and meeting records
Week 4 – Database & Data Preparation | Create database/backend structure and basic API | Clean dataset, remove duplicates/missing values and perform basic analysis | Review requirements against database/features and prepare test scenarios | Document database/data-processing approach
Week 5 – Development Sprint 1 | Develop homepage, search and basic navigation | Analyse destination features and prepare recommendation-related data | Review developed features and start functional testing | Document development progress and update report
Week 6 – Development Sprint 2 | Implement recommendation functionality, filters and destination pages | Test/validate recommendation data and support recommendation logic | Create detailed test cases, execute tests and record defects | Update implementation, testing and progress sections
Week 7 – Integration & Testing | Fix bugs and integrate frontend, backend and recommendation system | Validate recommendation results and data accuracy | Perform system, usability and integration testing; report bugs | Complete report sections, screenshots and testing evidence
Week 8 – Finalisation | Final bug fixes, UI improvements and GitHub cleanup | Final data validation and prepare analysis results | Perform final testing, UAT and regression testing; prepare test summary | Finalise report, references, screenshots and presentation material